## Test Case
Test Case ID | Test Case Summary | Pre-condition | Test Description | Test Data | Test Type | Expected Result | Planned Execution Date | Actual Execution Date | Actual Result | Status | Tester Name | Remark
TC_VWO_001 | Valid Login Credentials | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Login with a valid email and password | 1. choudhurys233@gmail.com 2. Kubul@1234 | Positive | User should be successfully logged in and redirected to the dashboard. | 2025-03-09 | 2025-03-09 | User successfully logged in and redirected to the dashboard. | Pass | Sudhansu Choudhury
TC_VWO_002 | Invalid Login Credentials | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Login with an invalid email or password. | 1. choudhurys2@gmail.com 2. Kubul@1234 | Negative | User should not be allowed to Logged in the page and will get a standard validation as "Your email, password, IP address or location did not match" | 2025-03-09 | 2025-03-09 | User is not allowed to Logged in the page and will get a standard validation as "Your email, password, IP address or location did not match" | Pass | Sudhansu Choudhury
TC_VWO_003 | Empty Email Field | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Attempt to login without email field and a valid password. | 1. Blank Email 2. Kubul@1234 | Negative | User should not be allowed to Logged in the page and will get a standard validation as "Your email, password, IP address or location did not match" | 2025-03-09 | 2025-03-09 | User is not allowed to Logged in the page and will get a standard validation as "Your email, password, IP address or location did not match" | Pass | Sudhansu Choudhury
TC_VWO_004 | Empty Password Field | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Attempt to login with a valid email and without password field. | 1. choudhurys233@gmail.com 2. Blank Password | Negative | User should not be allowed to Logged in the page and will get a standard validation as "Your email, password, IP address or location did not match" | 2025-03-09 | 2025-03-09 | User is not allowed to Logged in the page and will get a standard validation as "Your email, password, IP address or location did not match" | Pass | Sudhansu Choudhury
TC_VWO_005 | Empty Login Credetials | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Attempt to login without Credential | Both Field should be Blank | Negative | User should not be allowed to Logged in the page and will get a standard validation as "Your email, password, IP address or location did not match" | 2025-03-09 | 2025-03-09 | User is not allowed to Logged in the page and will get a standard validation as "Your email, password, IP address or location did not match" | Pass | Sudhansu Choudhury
TC_VWO_006 | Password Masking | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify if the password is masked (hidden) in the password field. | 1. choudhurys233@gmail.com 2. Kubul@1234 | Positive | The password should be visible in (•) format with Eye Button option. | 2025-03-09 | 2025-03-09 | The password is visible in (•) format with Eye Button option. | Pass | Sudhansu Choudhury
TC_VWO_007 | Eye Button Action | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify password unmasked post clicking on the Eyebutton | 1. choudhurys233@gmail.com 2. Kubul@1235 | Positive | Eye button should be visible and post clicking on the Eyebutton the Password shoul be unhide | 2025-03-09 | 2025-03-09 | Eye Button is disapear, post clicking outside of the password field. | Fail | Sudhansu Choudhury
TC_VWO_008 | "Forgot Password" Link | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Click on the "Forgot Password" link to reset the password. | Click on Forgot Password Link |  | 1. User should be directed to the password reset page. & have an Email address field to send the Password Reset Link | 2025-03-09 | 2025-03-09 | 1. User is directed to the password reset page & have an Email address field to send the Password Reset Link | Pass | Sudhansu Choudhury
TC_VWO_009 | Verify the Page Allignment | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify that the page allignment including input fields, buttons, and links, are properly aligned. | VWO Login & SignUp page |  | All the fields allighments should be in place | 2025-03-09 | 2025-03-09 | All the fields allighments are in place | Pass | Sudhansu Choudhury
TC_VWO_010 | Verify the compatibility of the website | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify that the login page works correctly on different browsers (Chrome, Firefox, Edge). | 1. Login to VWO in different browsers |  | User should be able to access on different browsers. | 2025-03-09 | 2025-03-09 | User is able to access on different browsers. | Pass | Sudhansu Choudhury
TC_VWO_011 | Verify the the website is open in different the Devices | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify that thewebsite and it's functionality on different devices (Windows, Android, IOS) | 1. Search and loginthe VWO website with different devices |  | User should be able to access on different devices | 2025-03-09 | 2025-03-09 | User is able to access on different devices | Pass | Sudhansu Choudhury
TC_VWO_012 | Signup for a full-featured trial | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify the Sign Up for new user | 1. xyz@gmail.com |  | 1. Don't have an account? Start a free trial should be visible to the end user 2. "Start a free trial" should be in hyperlink format 3. Post Clicking on the hyperlink user should be redirect to signup page 4. There should be an field as "Business Email" to enter the Mail ID for Signup 5. Post selecting the "I agree to VWO's Privacy Policy & Terms" Create Free Trail option should be actionable" | 2025-03-09 | 2025-03-09 | 1. Don't have an account? Start a free trial is visible to the end user 2. "Start a free trial" is in hyperlink format 3. Post Clicking on the hyperlink user is redirect to signup page 4. There is an field as "Business Email" to enter the Mail ID for Signup 5. Post selecting the "I agree to VWO's Privacy Policy & Terms" Create Free Trail option is actionable" | Pass | Sudhansu Choudhury
TC_VWO_013 | Signup for a full-featured trial | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify the Sign Up for new user without selecting the Privacy policy | 1. xyz@gmail.com | Negative | 1. Don't have an account? Start a free trial should be visible to the end user 2. "Start a free trial" should be in hyperlink format 3. Post Clicking on the hyperlink user should be redirect to signup page 4. There should be an field as "Business Email" to enter the Mail ID for Signup 5. Leave the "I agree to VWO's Privacy Policy & Terms" | 2025-03-09 | 2025-03-09 | Create Free Trail option is not clickable without selecting the privacy policy | Pass | Sudhansu Choudhury
TC_VWO_014 | Signup for a full-featured trial | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify the Sign Up for new user withexisting User Mail ID | 1. choudhurys233@gmail.com 2. Click on Create Free Trail option |  | 1. Don't have an account? Start a free trial should be visible to the end user 2. "Start a free trial" should be in hyperlink format 3. Post Clicking on the hyperlink user should be redirect to signup page 4. There should be an field as "Business Email" to enter the existing user Mail ID for Signup 5. Click on the "I agree to VWO's Privacy Policy & Terms" 6. Post Clicking on Create on free Trail option user should get a validation as "An account with this email already exists." | 2025-03-09 | 2025-03-09 | 1. Don't have an account? Start a free trial to the end user 2. "Start a free trial" is visible in hyperlink format 3. Post Clicking on the hyperlink user redirect to signup page 4. There is an field as "Business Email" to enter the existing user Mail ID for Signup 5. Clicked on the "I agree to VWO's Privacy Policy & Terms" 6. Post Clicking on Create on free Trail option user got a validation as "An account with this email already exists." | Pass | Sudhansu Choudhury
TC_VWO_015 | Sign In Using SSO | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify that clicking on "Sign in using SSO" redirects to the Single Sign-On login page. | 1. choudhurys233@gmail.com | Positive | The user should be redirected to the login page after clicking "Sign in using SSO." | 2025-03-09 | 2025-03-09 | The user redirected to the login page after clicking "Sign in using SSO." | Pass | Sudhansu Choudhury
TC_VWO_016 | Remember Me Functionality | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Check the "Remember Me" option while logging in and close the browser. | 1. choudhurys233@gmail.com 2. Kubul@1239 | Positive | User should be automatically logged in when returning to the website. | 2025-03-09 | 2025-03-09 | User is automatically logged in when returning to the website. | Pass | Sudhansu Choudhury
TC_VWO_017 | Verify Product selection Dashboard | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | After logging in, verify if the user is redirected to the page where all the VWO products are available | 1. choudhurys233@gmail.com 2. Kubul@1239 |  | The user should redirected to the product page and below products should be visible for selection • VWO Testing • VWO Insights – Web • VWO Insights - Mobile App • VWO Personalize – Web • VWO Rollouts – Web • VWO Feature Management • Backend server infrastructure | 2025-03-09 | 2025-03-09 | The user is redirected to the product page page and below products is visible for selection • VWO Testing • VWO Insights – Web • VWO Insights - Mobile App • VWO Personalize – Web • VWO Rollouts – Web • VWO Feature Management • Backend server infrastructure | Pass | Sudhansu Choudhury
TC_VWO_018 | Verify user redirect to Dashboard without Product selection | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify if the user is redirected to the dashboard page without selecting any VWO product | Login with valid credential & Click on Next without selecting any product | Negative | "Next" button should be disbled | 2025-03-09 | 2025-03-09 | "Next" button is disbled | Pass | Sudhansu Choudhury
TC_VWO_019 | Verify user redirect to Dashboard without Product selection | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify if the user is redirected to the dashboard page with selecting "VWO Testing" product | Login with valid credential & Click on Next withselecting "VWO Testing" | Positive | 1. User should be redirect to Dashboard with "Welcome to VWO!" massgae 2. Choose one to connect option should be visible 3. Post Selecting the Connect option suer should get an option "Add domain name" | 2025-03-09 | 2025-03-09 | 1. User is redirect to Dashboard with "Welcome to VWO!" massgae 2. Choose one to connect option is visible 3. Post Selecting the Connect option suer got an option "Add domain name" | Pass | Sudhansu Choudhury
TC_VWO_020 | VWO Chrome Extension popup visibility | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify that the "VWO Chrome Extension" installation option is displayed correctly. | 1. Check for the "VWO Chrome Extension" installation option 2. Verify that it is displayed correctly | Positive | The "VWO Chrome Extension" installation option should be displayed correctly. | 2025-03-09 | 2025-03-09 | The "VWO Chrome Extension" installation option is displayed correctly. | Pass | Sudhansu Choudhury
TC_VWO_021 | Create Test from Dashboard | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify to create test under "Active Tests" in dashboard page | 1. Login with valid credentials 2. Go to Dashboard 3. Click on "Create Test " under Active Tests | Positive | 1. Post clicking on Create Test Case "Create new campaign" page should appear 2. Create new campaign should have option to fill "Campaign name", "Platform" & "Campaign type" 3. Post selecting user should able to create Test. | 2025-03-09 | 2025-03-09 | 1. Post clicking on Create Test Case "Create new campaign" page should appear 2. Create new campaign has option to fill "Campaign name", "Platform" & "Campaign type" 3. Post selecting user should able to create Test. | Pass | Sudhansu Choudhury
TC_VWO_022 | Cancel funtionality at at Dashboard at Create Test option | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify the Cancel option should work to create test under "Active Tests" in dashboard page | 1. Login with valid credentials 2. Go to Dashboard 3. Click on "Create Test " under Active Tests | Positive | 1. Post clicking on Create Test Case "Create new campaign" page should appear 2. Create new campaign should have Cancel button 3. Post clicking on Cancel button user should be remain on dashboard page | 2025-03-09 | 2025-03-09 | 1. Post clicking on Create Test Case "Create new campaign" page should appear 2. Create new campaign has Cancel button 3. Post clicking on Cancel button user is remain on dashboard page | Pass | Sudhansu Choudhury
TC_VWO_023 | Create Test from Dashboard | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify to create test under "Active Tests" in dashboard page | 1. Login with valid credentials 2. Go to Dashboard 3. Create A/B Tests | Positive | 1. Post clicking on Create Test Case "Create new campaign" page should appear 2. Create new campaign should have option to fill "Campaign name", "Platform" & "Campaign type" 3. Post selecting user should able to create Test with A/B Tests option 4. Test Creation user redirect to Testing page | 2025-03-09 | 2025-03-09 | 1. Post clicking on Create Test Case "Create new campaign" page is appear 2. Create new campaign has option to fill "Campaign name", "Platform" & "Campaign type" 3. Post selecting user is able to create Test with A/B Tests option 4. Test Creation user redirect to Testing page | Pass | Sudhansu Choudhury
TC_VWO_024 | View of Testing Tab | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify to create test under "Active Tests" in dashboard page | 1. Login with valid credentials 2. Create A/B Tests | Positive | 1. Test Creation user should redirect to Testing page 2. Sample Report should be visible with Paused, +Create, Sort by, Campaign details & other parametter should be visible at Testing page | 2025-03-09 | 2025-03-09 | 1. Test Creation user redirect to Testing page 2. Sample Report is visible with Paused, +Create, Sort by, Campaign details & other parametter is visible at Testing page | Pass | Sudhansu Choudhury
TC_VWO_025 | Create a New Campaign | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Click on the "Create Campaign" button and fill out the necessary details (e.g., campaign name, target audience, etc.). | 1. Go to Testing 2. Click on +Create | Positive | The campaign should successfully created and appears in the campaign list. | 2025-03-09 | 2025-03-09 | The campaign is successfully created and appears in the campaign list. | Pass | Sudhansu Choudhury
TC_VWO_026 | Pause a Running Campaign | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Pause a running campaign from the dashboard. | 1. Go to Testing 2. Select anyone campaign 3. Click on Pause | Positive | 1. The campaign should be paused and the status should update to "Paused." 2. Start option should be visible near Paused option | 2025-03-09 | 2025-03-09 | 1. The campaign is paused and the status is update to "Paused." 2. Start option is visible near Paused option | Pass | Sudhansu Choudhury
TC_VWO_027 | Account/ Profile Information verification | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify that the account information is displayed correctly in the top-right corner in User Menu | 1. Check the top-right corner User Menu 2. Click on Edit profile 3. Verify the Account | Positive | The account information should be displayed correctly | 2025-03-09 | 2025-03-09 | The account information is displayed correctly | Pass | Sudhansu Choudhury
TC_VWO_028 | Need help option functionality | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify that the "Need Help?" button provides relevant informations | 1. Click on the "Need Help?" button | Positive | The "Need Help?" button should provide relevant information to contact or chat | 2025-03-09 | 2025-03-09 | Continuious Loading. No details are visible post clicking on "Need Help?" | Fail | Sudhansu Choudhury
TC_VWO_029 | Setting option Funtionality | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify that the settings functionality in the top-right corner | 1. Click on the settings icon in the top-right corner | Positive | 1. User should be redirect to Account setting page post clicking on Setting Icon | 2025-03-09 | 2025-03-09 | 1. User is redirect to Account setting page post clicking on Setting Icon | Pass | Sudhansu Choudhury
TC_VWO_030 | Account Verificat functionality | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify that clicking on "Verify Account" initiates the account verification process. | 1. Click on "Verify Account" | Positive | 1. Post clicking on "Verify Account" below massage should appear with "Ok & Resend Email Option" "Verify your account Access to some features is blocked until you verify your account. Please verify your account by clicking on the confirmation link on the email sent to you. A verification email was sent to mail@gmail.com | 2025-03-09 | 2025-03-09 | 1. Post clicking on "Verify Account" below massage appeared with "Ok & Resend Email Option" "Verify your account Access to some features is blocked until you verify your account. Please verify your account by clicking on the confirmation link on the email sent to you. A verification email was sent to mail@gmail.com | Pass | Sudhansu Choudhury
TC_VWO_031 | Logout option funtionality | 1. Open Search Enginee like Chrome/ EDGE 2. Search for https://app.vwo.com/#/login | Verify Logout option should be work ASIS | 1. Click on Edit the Profile 2. Click on Logout | Positive | 1. User should be Logout successfully and redirect to login page | 2025-03-09 | 2025-03-09 | 1. User is able to Logout successfully and the page redirected to login page | Pass | Sudhansu Choudhury

## Defect
Defect_ID | Test Case ID | Module | Defect Desciption | Step To Reproduce | Severity | Type | Date | Status | Raised By | Resolved Date | Remark
D_001 | TC_VWO_007 | VWO Login Page | Eye Button is disapear, post clicking outside of the password field. | 1. Filll Password 2. Click on Eye button to see the full password 3. Then Click outside of the box 4. Again Try to click on Eyebutton | Medium | Functional | 2025-03-09 | Open | Sudhansu
D_002 | TC_VWO_028 | VWO Login Page | Continuious Loading. No details are visible post clicking on "Need Help?" | 1. Login to VWO page 2. Click on "Need Help?" | Major | Functional | 2025-03-09 | Open | Sudhansu